## Slide 1: Kick-Off Meeting Belgrade, 11 – 12. July 2022
Coordinator: Prof. Dr. Sinisa Djurasevic
Institution: University of Belgrade

## Slide 2: Responsabilites/Roles
All Project partners will participate and contribute to all project activities. In addition, UB will:
  Be responsible for the organisation of both a kick-off and a final conference and lead overall Project management;
  Chair the Project Management Group, perform day-to-day Project activities coordination and financial administration, and bookkeeping to the highest standard. They will include upholding contractual agreements that individual Project partners will sign at the start of the project, dispersing project funds, monitoring consortium member adherence to project work plan;
  Be the ultimate authority in decisions concerning fiduciary matters coordinating and monitoring all Project activities, reviewing materials before publication, reviewing all project reports, and maintaining communication with Project partners concerning financial matters, project implementation, and contractual agreements matters, when appropriate;
  Lead all Project results dissemination activities.

## Slide 3: Responsabilites/Roles
FHJ will:
  Be responsible for leading overall Project quality assurance;
  Chair the Quality Assurance Group;
  Prepare a draft of Project quality assurance standards and procedures that Project partners will adopt at kick-off meeting;
  Organise the quality control of all Project activities and results that will be continuously performed during the project realisation;
  Lead analysis of the MCs implementation practices in the Project partners states;
  Lead implementation of all Project results in the Guidelines.

## Slide 4: Responsabilites/Roles
ACEEU will:
  Lead analysis of the MCs certification and credit evaluation practices in the Project partners states;
  Lead analysis of the MCs accreditation and quality assurance practices in the Project partners.
UDL will:
  Lead analysis of the MCs legal frameworks in the Project partners states;
  Lead analysis of the linking MCs to NQF in the Project partners states, with the QAS specific role regarding linking MCs to the NQF in Serbia.

## Slide 5: Overview of project activities and results
ID. | Meeting/Activity Title | Leading organisation/Place of Venue | Date | Results/Responsible organisation
1. | Kick-off meeting | University of Belgrade (UB), Belgrade, Serbia | 2022-03 | 1. Setting-up of Project bodies 2. Adoption of the document on the way of work 3. Dissemination agreement (web page, Guidelines) 4. Reschedule of activity timetable 5. Report (UB)
2. | Training on the MCs implementation practice in Partner HE | FH JOANNEUM GESELLSCHAFT MBH (FHJ), Gratz, Austria | 2022-06 | 1. Analysis (FHJ) 2. Report (FHJ)
3. | Training on the MCs legal framework practice in Partner HE | UNIVERSIDAD DE LLEIDA (UDL), Lleida, Spain | 2022-09 | 1. Analysis (UDL) 2. Report (UDL)
4. | Training on the MCs certification and credit evaluation practice in Partner HE | ACEEU GmbH (ACEEU), Munster, Germany | 2022-12 | 1. Analysis (ACEEU) 2. Report (ACEEU)
5. | Training on the MCs accreditation and quality assurance practice in Partner HE | ACEEU GmbH (ACEEU), Munster, Germany | 2023-03 | 1. Analysis 2. Report (ACEEU)
6. | Training on the linking MCs to NQF practice in Project Partner HE | UNIVERSIDAD DE LLEIDA (UDL), Lleida, Spain | 2023-06 | 1. Analysis (UDL) 2. Report (UDL)
7. | Training on the implementation of all Project results in the Guidelines | FH JOANNEUM GESELLSCHAFT MBH (FHJ), Gratz, Austria | 2023-11 | 1. Guidelines (FHJ) 2. Report (FHJ)
8. | Final conference | University of Belgrade | 2024-01 | 1. Report (UB)

## Slide 6: Project bodies and documents
Project Management Group (one member per Institution)
  UB as Chair
Quality Assurance Group (one member per Institution)
  FHJ as Chair
Project quality assurance standards and procedures
  Proposed by FHJ and accepted by all Partners

## Slide 7: Activity timetable rescheduling
ID. | Meeting/Activity Title | Date (old/new) | Results | Date (old/new)
2. | Training on the MCs implementation practice in Partner HE | 2022-06 07-11.11.2022 | Analysis of the MCs implementation practice in each Partner country, making a list of examples of good Practice (all Partners/FHJ) | 01.02-30.06.2022 23.07-23.10.2022
3. | Training on the MCs legal framework practice in Partner HE | 2022-09 29.11-03.12 | Analysis of the legal framework in each Partner country, making a proposal for a best legislative model (all Partners/UDL) | 01.06-30.09.2022 15.08-15.11.2022
4. | Training on the MCs certification and credit evaluation practice in Partner HE | 2022-12 31.01-04.02.2023 | Analysis of the MCs certification and credit evaluation practice in each Partner country, making a proposal for the best model of certification and credit evaluation (all Partners/ACEEU) | 01.09-31.12.2022 17.09-17.12.2022
5. | Training on the MCs accreditation and quality assurance practice in Partner HE | 2023-03 27-31.03.2023 | Analysis of the MCs quality assurance practice in each Partner country, making a proposal for the best model of MCs accreditation (all Partners/ACEEU) | 31.12.2022-31.03.2023 13.12.2022-13.03.2023
6. | Training on the linking MCs to NQF practice in Project Partner HE | 2023-06 22.-26.05.2023 | Analysis of the linking MCs to NQF in each Partner country, making a proposal for the best model of linking (all Partners/ UDL) | 01.03-30.06.2023 08.02-08.05.2023
7. | Training on the implementation of all Project results in the Guidelines | 2023-11 To be defined | Implementation of all analysis results and proposals in the Guidelines (all Partners/UB) | 01.07-31.10.2023 To be defined
Project Start Date - 01-02-2022 Project End Date - 01-02-2024

## Slide 8: Analysis principles
User friendly (they must be understandable to people outside of higher education), but:
  must have all the indicators on which the analysis was done (the number of HE institutions, the number/name of the MCs, the principles of the legal framework and the name/definition of the laws, the principles of the accreditation process and the bodies dealing with it, etc.
Will consist of:
  Introduction
  Analysis (per country, made by all Partners);
  Conclusion (made by Leading Partner)
    list of examples of good Practice
    proposal for a best model
      Conclusions can be one for all Partners or different per country

## Slide 9: List of MCs examples of good Practice (a proposal)
MCs name
HE Institution (name, city, country)
ECTS number
The competent law
Accreditation body/bodies
Link to the NQF
Recognition (ENIC/NARIC or any other body)
Horizontal mobility (both upward and backward)
Curriculum

## Slide 10: Not to forget development of 3 micro-credentials
Development of 3 micro-credentials examples that will serve as a proof-of-concept
  Theoretically developed or present in practice?
  They can belong to any of the Partner countries, either to the HEI which is Project partner, either to any other
  A possibility for the Project third year extension?

## Slide 11: Any other idea?
ISCED/ISCO codes
Horizontal mobility of MCs students (both upward and backward)
  To and from BSc
  To MSc (in case of previous BSc 240 ECTS completition)
MCs as the way to the HE entrance for students who otherwise would not be able to do so
  In Serbia, a prerequisite for enrollment in higher education is to have completed a four-year secondary school, which prevents students from three-year vocational secondary schools from participating in HE
  Can the completed 60 ECTS through MCs be considered as a substitute for the missing year of high school

## Slide 12
Thank you for your attention
Vielen Dank für Ihre Aufmerksamkeit
Gracias por su atención
sine@bio.bg.ac.rs
www.bio.bg.ac.rs